## Sheet1
Corporate Communications Unit WIP Meeting Project | Actions | Update 21 May | Update 18 June | Update 2 July | Update 17 July | Update 30 July | Update 13 August | Update 28 August | Update 10 Sep | Update 25 Sep | Update 9 Oct
Business Unit Plan 18/19
Internal communication
· Inside City | · May with design – Friday release (digital) | Content to Edwin on Monday | Content for the July issue due on 20 June. Send content to Amy by then. | July issue due to go out this week. August content is due by 19 July. | August content due 19 July. | Partial content sent to designers, remainder will be sent today. | August issue with printer. Planning September issue. | Working on September issue, but missing some content. | Working on October content. Will need to push this one through a week early (Annual Leave). | Still working on October content. | October with graphic design for final changes. November content due 21 October.
CEO Column - Eric resigning (new Commissioner to come in)
· Intranet redevelopment | · Roadmap priority – speed. DAI prioritization session on 13 June to determine actions. Survey report prepared for ELT 8 May | SHC invited to prioritisation session | Intranet Version 2.0 as a 'should do' for Q3. Will meet with DAI possibly next week. | DAI is busy with ProMapp project. Some other projects may slip to Q4, including the Intranet. | Some items will be done as BAU. Need to liaise with DAI. | No update. | No update. | Videos removed to help increase performance. Looking at other options with IT/DAI. | DAI looking to see whether the Hero News panel can be updated. | No Update | No update.
· Internal Communications Plan |  |  | Update required for 2018/19. | Update still required for 2018/19. | Update still required for 2018/19. | No update. | No update. Need to add matrix. | No update. Need to add matrix and new channels. | No update. Overdue. | No update. Overdue. | No update. Overdue.
· Annual Report | · No update. |  | Planning underway. Content due 12 July. Simone to send email to all managers reminding them of deadline. Aiming for sooner than December. | Simone has emailed managers and I am starting to work with staff from each unit. | Need to follow up outstanding content. | No update. | Working on draft content for ELT consideration. | Working on content and liaising with STP. | Working on content. Overdue. | Working on content. Overdue. | Working on content. Overdue.
· Curtin University Graduate Scheme events | · AT to draft content for HR. |  | No update. | No update. | No update. | No update. | No update. | No update. | Included in October Inside City. | No response from HR. | No response from HR.
· HR Improvement Plan | · Corp announcement and Inside City June |  | Not included in June Inside City due to space restrictions. | Promoted via Intranet and July Inside City. | [5 empty] | Complete.
· HRIS launch |  |  | Communicated through email, Inside City and Intranet. Ongoing. | My HR was launched on Monday. Working with project team on teething issues. | First pay cycle successful. Communications ongoing. | Communications ongoing (education). | Communications ongoing (education). | Need more communications around Payroll. | Need more communications around Payroll. | Ongoing | Minor changes coming. Pay in advance option for annual leave will be removed.
· Corporate Recovery |  |  | Staff briefing sessions this week. Changes to Intranet pending. Managers and Directors meeting with Teams post CEO session. | Chris Noble to advise changes to Intranet. Survey will be released on 5 July, closes 26 July. | CRIP 2.0 released this week. | No update. | Preparing introductory bios for new GMs. Working with Karin/Chris to update Intranet pages. | Working with Karin/Chris to update Intranet. Preparing a 'meet the GM' piece for Inside City. Major work will be needed to up-date Intranet to new portfolio model. | Ongoing. | Ongoing | Ongoing.
· Procure to Pay |  |  |  |  | Invoices due by 19 July. System will launch on 24 July. | Communications ongoing (education). | Communications ongoing (education). | No update. | No update. | Ongoing | Changes coming to how goods receipts are actioned.
· Inquiry Panel | [5 empty] | Staff survey released on 23 July. Closes on 1 August. | Follow up survey planned for October. | Preparing positive stories and keeping staff informed. | Ongoing. | Ongoing | Ongoing.
· Pulse Check Survey | [9 empty] | Second survey will go out in mid-October. | Confirming survey questions. Scheduled to go out 21-30 October.
Upcoming/Other
· Employee Culture Survey (Your Say Survey) | · September | [5 empty] | Comms started. | Survey will go out on 2 September. | Survey open to 20 September. | Survey closed. Results will be communicated by HR. | Changes will be communicated in November by Human Resources. A summary will need to be included in the December issue of Inside City.
· Weekly positive story for staff (flu shots, road safety week)
· Comms Plan drafted (September survey)
· August launch (feedback provided by ICO)
· Videos on Intranet homepage
· Inside City, Hero News, staff event, HR induction
· NAIDOC Week |  |  |  | Staff event on 11 July. Promoted through Inside City and Intranet. | Follow up article planned for Inside City August. Video will be used on the Intranet once completed.
· PPMS |  |  |  | Gateways has been decommissioned, PPMS will go live later this month. Communicated via Intranet and Inside City
· CEO Recognition Awards | [6 empty] | Regular comms planned. | Regular comms planned. | Nominations close on 13 September. | Awards being presented 3 October. | Awards delayed as CEO was on leave.
· Safe Work Month | [10 empty] | Inside City article, Hero News story on Intranet.
· Staff Christmas Party | [6 empty] | Comms planning underway. | Working with Civic Services to promote. | No update. | No update. | Advertised to staff through Inside City and Intranet.
Strategic Community Plan
· Internal Communications Survey | [10 empty] | #NAME?
Media relations
· Overview of last two weeks | · CCTV/Smart cities – Friday | * Exec recruitment for GM roles (22 May) | Facial recognition implementation | Wall collapse at the Library Nightclub | 6PR interview with Eric and following fallout | FTE Article | Inquiry coverage |  |  |  | tender - report accessible by panel - TBC - could be delayed by two months.L47
| · Meltwater – tender being reviewed this year |  | May Monthly Media Report compiled and issued | Paving issues at Wellington St crossing | EDU budget breakdown provided to Sunday Times | City Revitalisation article | New Chair and Commissioner
| · City Planning Strategy |  | Draft City Planning coverage in The West and in Guardian Express | RFQ - Media Services | Liza Harvey on 6PR - Homelessness | Instagrammer article | Questions regarding homelessness
| Citizen science |  | Pedestrian overpass collapse | Public Information Response Group meeting | City Planning Strategy Interview - Robert Farley | Homelessness
| Today Tonight - PCEC carpark |  |  |  | Parking Fines, Stats and legal representation - WA Today | Stress Leave Enquiry
[5 empty] | Royal St Free Parking Trial Launch | OHS Media Enquiry
The Heights filming proposal supported and actions underway
Media unit roles and responsibilities provided to CT for Intranet page
|  |  |  | The Heights filming proposal support | Ch9 I/V Andrew Hammond - Homelessness
· Pending releases | · Homelessness Accreditation | Council meeting 28th - sponsorship | Homeless Accreditation - final objective of identifying a place to offer services in one place. Hoping for this to be implemented 1 July, coinciding with new financial year. Haven't firmed up the location to operate from. Going ahead with uniting the services. | Kings Hotel public art project | MOU Media release - Joint Tourism Marketing | No Update
| · Key Sector Sponsorship | * Interview with ABC (Dan High) - facial recognition (24 May) | Key Sector Sponsorship Study Perth from the Agenda Briefing | Public Sector Awards - City awarded the Best Practice | Agenda Settlement - Event Sponsorships | In progress + addition of grant round opening | Pending endorsement and approval
| · Heritage Perth |  | Heritage Perth - Caitlin and Michael to liaise on this. | in Public Sector Evaluation - a bit dry, might be LinkedIn | Agenda Settlement - Parklet Trial Outcomes |  | Agenda Settlement releases
| · Opera in the Park |  | Opera in the Park from the Agenda Briefing | Get an update on Homeless Accreditation | Agenda Settlement - Homelessness Plan
|  |  | Ongoing | Tender delayed - TBC | Agenda Settlement - ATP Cup Sponsorship
[5 empty] | Media Release - Outdoor Dining changes implemented 1/8 | In progress
Kings Hotel Art Installation photo opp
· Upcoming work in progress |  | * Eric leave | City support for series two of The Heights
|  |  | Media Monitoring Guidelines |  | RFQ
|  |  | Council Meeting 25/6 |  | Media Release - Budget adoption
|  |  | My Media meeting (media service provider) |  | June Monthly media report to be compiled
|  |  | Isentia meeting (media service provider) |  | Homelessness/Retail Notice of Motion
|  |  | Meltwater meeting (media service provider) |  | Homelessness Accreditation
· Upcoming: Team calendar 18/19 |  |  | May (Edit) Monthly Media Report
CCTV
Communication projects
| · NAIDOC Week - 11 July – Internal event | NRW interview - ABC I/V with Gaye for Sunday morning | Will place up a featured news story on 20 June | Featured news story has been up on the intranet for the past two weeks. Shahna has mentioned 90 people have confirmed their attendance. | NAIDOC Week internal staff event was a success. A writeup will be included in Inside City along with selected images. There's a wrap-up story on the intranet too.
RAP | · NAIDOC Week internal installation |  | All running smoothly - due to be installed on 7 July early morning | Will meet the artist in the morning of 8 July for set up. | Internal installation was installed at the beginning of NAIDOC Week. We have decided to leave the installation up for a couple more weeks. | Will leave up until the exhibition finishes in September. | No update as per 30 July | The internal installation is still up. I will look to get Nadia to take this down in the coming weeks. Unless we want to leave it up. |  | This continues to stay up due to the requests. Jordan Nix looking into something similar for PRIDE.
| · NAIDOC Week media release scheduled for w/c 1 July | Internal staff event next week | With ACH for final approvals and will send to Simone once done. Will also send to Amy to replicate for Inside City | The NAIDOC Week media release was distributed on 27 June. | NAIDOC Week media release sent. Coverage in the Subi Post.
| · Innovate RAP in progress |  | Have put together a small story in Inside City on the draft Innovate RAP workshop | Working with Shahna on a Comms Plan before launch in September. | Have met with Shahna to discuss comms around this. Will look at putting together a draft Comms Plan as they are looking at the launch of the Innovate RAP as early as October. | In progress - will look to Shahna to send through the draft innovate RAP so I can populate dates. | Will start to look at the Innovate RAP comms plan when Shahna is back from leave in September. | As per update 13 August |  | Haven't been updated via CMS yet but hopefully we are notified soon so I can put a comms plan together
| · WALGA RAP Poster |  |  |  |  | Steph has sent the RAP WALGA Poster to Shahna, Bek and Kathleen for approval. Wording has been sent through via comms.
| · Street banners |  | All approved and ready to be sent to the printers via James/Rachel | Completed. | Completed and are up on St Georges Terrace | Have sent Sam in digital content to include, and hopefully Thom will be able to take a few photos soon. | Thom has taken photos on Monday - hope to place social content up this week. | Following the photos Thom took of the banners, a LinkedIn Post was placed up last Friday. There was a high rate of engagement with 150 likes and more than 20 comments (all mostly positive)
| · Printing out NAIDOC Week posters for amenity frames |  | Will print out for the w/c beginning? | Completed.
| · Yokai consultation: Stolen Generation |  |  | Working with Jen Walsh on this one.
| · Aboriginal artwork |  |  | Have organised a photo shoot with the Commissioners, CEO, artist, ranger and WAC officer for next Thursday 11 July at 1.45pm. This will be published in the Sunday Times. Will use the images for Perth City Local, City News and Inside City/Annual Report, too. Working with Thom today to get some internal shots done. | Photo taken with the Sunday Times on Thursday but the story was not printed in last Sunday's paper. Have since sent out a media release utilising the photo taken on Thursday and will place a story in Inside City, Perth City Local and City News. | This has received a run in the Koori Mail - a National newspaper.
| · Evaluation Report - Reflect |  | BH working on putting this together | Ongoing. | In progress. | In progress. | Waiting on photos of the street banners to finish the Reflect Evaluation Report. | Evaluation Report complete and with CT for review. |  | Completed - BH to send to Ben.
One hour free parking trial | · Write QandA's for use across all avenues |  |  | BH has written these and sent them off to PSU and Transport. | A photo was taken on Monday with the three Commissioners, businesses and the East Perth Community Grouop. This was sent to Perth Voice and Community News for use. | Complete, until the trial moves to another part of the City. Will keep in contact with the project team on this one. | Media release sent on Monday in regards to East Perth launch. Coverage in The West Australian, Sunrise, Nova and 6PR. Will start to put together West Perth media release and determine opportunities for 9 September launch. | West Perth free parking trial media release has been approved and I am looking to send this out tomorrow once the team confirm whether they are extending the trial to another couple of bays. Have organised a photo opp for Tuesday 3 September with West Perth Local, Commissioner Hammond and local businesses. Have pitched this to Peter at The West to see if they'd like to send a photographer down. |  | All one hour free parking trials are in place. Media was strong on this one. Perhaps look into doing something in six months to promote the economic benefit of the trials.
| · Prepare high level Comms plan |  |  | EG and BH have developed this and will work to it before the launch day of 15 July on Royal Street. | Completed.
Urban Forest Plan | · Working on a tree trail event for the school holidays |  | Looking like this will happen for the summer or even autumn school holidays as budget hasn't been approved yet. | Ongoing. | Ongoing. | Ongoing - working with Barbara to see if we can put together a holistic approach across a few BU's. | Had a meeting with Barbara this morning to determine tree trail logistics. | Put together a media release on the Urban Street Tree Infill award and sent that out last week. This was covered in Community. |  | Working with Barbara and Karl on ongoing UFP comms.
| · National Tree Day |  | Working with Karl on if the planting event will happen at Heirrison Island | National Tree Day planting in the City of Perth will happen at David Carr Memorial Park on 28 July. This will be communicated on the intranet and via Perth City Local. | Will put together a small media release focusing on National Tree Day and the amount of trees we have planted as part of the UFP. | NTD was very successful with quite a large turn out from last year. Will put something in Inside City. | NTD published in Inside City and on the Intranet | National Tree Day was covered in WALGA's Community and Place and Enviro News.
Water Sensitive Cities | · Waterwise Council | [6 empty] | The City was recognised for being a top Waterwise Council at the WALGA Convention. A media release was sent out and was covered in Community News.
Social Strategy | · Stakeholder Engagement Plan almost signed off. |  | Working with Kathleen on a small story for City News (and possibly Inside City) once stakeholder engagement begins in September | Social Strategy story drafted and sent to Tomi for inclusion in City News and Amy for inclusion in Inside City. | Social Strategy draft included in City News and in Perth City Local. Will use this to write a media release which I will make sure is sent outside of the Inquiry period. | The Social Strategy has been promoted on social media and a media release has been sent out. Approved content will also be published in Perth City Local and City News. | Continue to put together content for the Social Strategy, including an advertisement in the What's On. Kathleen has requested more content for socials to get people to nominate for the Community Reference Group. | Social Strategy internal and external comms still going strong. Need to push this as the survey closes on 30 September. Will look into further socials and intranet postings. |  | BH to put together a comms checklist for the Neighbourhood Engagement Workshops. BH to also supply MQ with copy for the Social Strategy survey extension for Perth City Local.
Strategic Community Plan
| · Pushed back to September |  | Chris to have a meeting with CT and BH on Thursday to fill us in. | Ongoing. | Ongoing. | Ongoing. | Ongoing. | Ongoing.
· Comms plan and SEP drafted
Integrated Parking Management Strategy | · Quote received, BH working through content |  | Waiting on Community Services to confirm the contract has been signed. QandA's and Comms Plan have been drafted. Meeting with the team scheduled for this week. | Still waiting on confirmation of contract signed. Waiting on Media QandA's to be sent back following approvals. This will form the content of all collateral going forward, including a City News article, piece in the Perth City Local August edition and a media release (distribution date 8 August) | Kristi has confirmed the pilot project will be launched on the 28 August. Hoping to send the media release out on 15 August. Waiting on approval of City News and media release content. | Kristi has yet to confirm the dates of the pilot project. Apparently the contract is being signed on 2 August and comms will begin the week of 9th or 30th September depending on what dates have been chosen for the pilot project. | IPMS has been cancelled and will be replaced with a well-thought-out parking upgrade. Internal staff will be updated once Murray makes the final decision. | Comms were used to update internal staff around the decision to cancel IPMS. Will work with Kristy at a later stage to put together a comms plan for a parking upgrade. |  | IPMS cancelled.
Rates notice brochure | · Council will adopt budget on 23 July. Aiming to send the Rates Brochure to print on 25 July. |  | BH to start adding in content and briefing design team. Will populate from year in review content (annual report and budget from last year) and Strategic Community Plan. BH to liaise with TE for August edition of Perth City Local. | Finance has now sent draft numbers through. BH to start to populate that into the design. | Michael Kent and Commissioner Lumsden working on changes. Steph was working on creating little icons for the budget page. Rachel taking over from Steph to make sure this is sent to Zipform on time (24 July) | Sent to print. | Have arrived at Council House. | Still to collect a box from Finance - will do this week. |  | Have approved goods receipt for Zipform to be paid.
City Planning Strategy | · Media release sent in early June | * drafted strategy, pending media release 29 May | BH has been pitching to media since media release was sent out, including a successful pitch to the Guardian Express. | BH helping City Planning with ongoing comms. | Rob Farley had an interview with ABC Perth on Monday afternoon. | Survey results will be going to Council in September. BH to prepare a high level comms plan around this. | Survey results will be going to Council in September. BH to prepare a high level comms plan around this. | Survey results will be going to Council in October now. Working on a high level comms plan around this. |  | City Planning Strategy draft feedback will be presented to council in October. BH to prepare comms around this one.
Joanne to send content through to Amy for Inside City before 20 June.
Cultural Development Plan | · Cultural Development Plan signed off by BH and CT. Waiting on final document to be uploaded on the website for HK to send the media release out. |  | BH working on comms plan for Cultural Development Plan Launch - inviting media etc. | Comms plan for Cultural Development Plan Launch with CT for approval. Launch is on 31 July. | Launch is now scheduled for late August - will update comms plan to reflect this. | Comms have been updated to reflect the launch date being late August. | List of media has been determined to invite to the launch. Invites will be sent out next week. BH to put together some high level QandAs around the cost of the event. | Media invites to the Cultural Development Plan have been sent out. Many journalists have declined but have requested a copy of the plan and I have sent them some briefing notes to go along with it. |  | BH sent through response to an enquiry from Community News journalist Michael Palmer regarding Perth Concert Hall. Will continue to promote the Cultural Development Plan where possible.
Homelessness and HSAP | [5 empty] | Homelessness Communications Plan with CT for approval. Media release on the Interim Homelessness Plan has been drafted and will be sent out Thursday 1 August. | Homelessness Communications Plan with CT for approval. BH preparing a media release to be sent out late next week with regards to the HSAP. | Homelessness Comms Plan with CT for approval. I am preparing a media release to be sent out in early October with regards to the HSAP going to September's Council rather than August. |  | Waiting on CMS to share details of when the HSAP will go to Council.
Wellington Square Masterplan | [5 empty] | Media release drafted on the state landscape award received on the weekend. This will be sent out Friday 2 August. | Media release on award sent and was picked up via Michael Palmer at Community News. | Covered in Community News. |  | Ongoing
ACH | Childcare mural |  |  | BH working with Lauretta on oral histories and podcats | Working on story for Childcare mural (tying in with National Aboriginal Children's Day) | Photo has been taken at the Childcare mural. Will use to promote in Inside City and on the Intranet. | Mural photos sent for use in Inside City | Will be used in this month's edition of Inside City. |  | Completed and promoted in Inside City.
| Perth Town Hall 150 | [5 empty] | Working with project group on timings for next year. Will put together a comms plan in due course. | As per last update. |  | Student putting together a film on the 150th anniversary which may air on Channel 7. Have put together some story ideas for City News and Perth City Local based off this discussion.
Blue Tree Project |  |  |  | BH working on Tides Swan River Stories evaluation report. | BH working on Tides Swan River Stories evaluation. |  | BH has put together a high level comms plan for Blue Tree Day in October. Will meet with the team next week to discuss further. | Continue to meet with team on Blue Tree Day. Have put together some internal messaging and have designed a poster for the amenity clipper frames. We use the internal messaging to create a media release and put together a list of people we might like to invite on the morning of the wrapping. |  | BH working with project team in ACH to put together comms for Blue Tree Day and Mental Health Week. Will work on a media alert for mid-next week and a media release scheduled for Friday 4 Oct. MQ to help BH disseminate photos on the Friday.
· Pride Parade |  |  |  |  | BH working on a Comms plan around this. | BH working on Comms plan around this. | Continuing to work on Comms plan for this. | Continuing to work on Comms plan for this. |  | BH working with the project team to put together an internal and external comms checklist to promote the City's involvment in the parade and to get staff on board.
Upcoming
· East End Revitalisation | · BH working on project plan and Comms plan |  |  | Comms plan with CT for approval. BH working on populating dates into project plan. | Comms plan with CT for approval. BH working on populating dates into project plan. | Comms plan with CT for approval. | Comms plan with CT for approval. | Comms plan with CT for approval. |  | Comms Plan with CT for sign off.
· Corporate Business Plan | · CN/Karin
Digital
· Solution Review/Health Check | · Nic provided health check response review - Analyse for next steps. |  | Brand actioning items this month | Brand edits to Content editor and componenets in UAT for approval | Brand edits to Content editor and components in UAT for approval |  | Current status being reviewed |  | DRM reviewied Major items Brand checking on status of ticket with Sitecore DRM reviewing Minor items | - Brand have confirmed they can not source the ticket they thought had been raised back in January - Are now raising this ticket | - In progress
| · Communicate Major items to Exec |  | With changes to Exec, this will be rolled into the Phase Two information
· Brand Contracts | · SLA – on hold. |  |  |  | Hold |  | Contract extension for a maximum 6 months agreed
· Publishing workflow | · Implemented but not yet switched on – role review |  | Brand working on role groupings after matrix provided | Roles meeting with Brand yesterday - supplying summaries | Summaries supplied. Awaiting feedback from Edin |  | Awaiting estimate from Brand |  | Worklfow for Cos and SMA in final stages - Awaiting clarification from us on areas of implementation | - Met with PH and NB re publishing and workflow work to date to provide feedback - Meeting coming up with As and NA to lock down SSO matching | - test of new workflow implemented to blog section for testing
| · SSO – AS assisting. |  | · SSO – AS assisting. |  |  |  | SSO – AS and DM assisting. |  | Meeting with Brand next week to discuss the issues with project |  | - SSO has been included in the detailed upgrade breif for Brand
· Website support | · Dave commenced last week |  | Dave progressing well through tickets and seeking additional improvements | As before | Awaiting response from AH on contracts |  | DM extended to January 31 |  | Ongoing | - Looking to fill support role asap | - Support role appointed via 303. Starting Thursday
| · Setting up Microsoft Teams for web support |  | Currently using Asana to organise work and use team chat | DAI have proposed an alternative to Asana |  |  | Further enhancing Teams site
· MVP close out | · Disaster recovery work ongoing |  | To be revisited next week | Completed | Technically not completed as workflow is elsewhere :(
| · Banners form to be live later this week |  | Completed
| · lighting form to begin after lighting repair |  | Lighting form removed from MVP delivery
· Think Perth | · Think Perth project management ongoing |  | Only two MVP items remain | Awaiting confirmation from JF on status | Decommissioning SBM site - in progress
Working with ED and Brand on retiring old SBM site
· Old site decommissioning | · Broken links project - 1300 on website |  | Has been on hold during MGs absence - Starting again this week | Booked time with MG on Friday | Edits made to site base don response from Managers |  | Coordination with records, ED and MKT on records |  | Complete from public facing | - met with MGK, AS, MV, MG, LH to determine risks and actin plan for old site retentions - agreed 15 year retention to old corporate site (Drupal) and tape storage of SBM | - The team in IT have had some database issues and struggling to spin up an instance. Currently being investigated.
| · IT to lead process |  |  |  | Public access to site now removed
· Web Chat | · Trial to start June |  | Trail ongoing. DM and MS meeting with CCU regularly to tweak as we progress. | Pilot for 12 months | Pilot strategy - Not started |  | Optimisation plan in development |  | New pages added after consultation with AH | - Exploring different options for web chat software to meet with Accessibility compliance | - No further updates
· Forms | · Working with MG and JJ on ODD forms – almost finished |  | ODD form is in soft launch phase | ODD form still in soft launch | ODD form still in soft launch |  | Awaiting further budget from AH for renewal enhancements |  | - Still waiting | - Added to Phase 2.2 | - Sitecore 9.2 selction as upgrade will enable enhanced form functionality, security and accessibility
| · Marketing looking for more reassurance on BP use |  | Portal out of scope for August full launch |  | Optimisation ongoing
· Data and Analytics | · DAI offered to support – Working with Amitesh on setup (Power BI dashboard) |  | DAI presenting solution this week | AI devel;oped dashboard. Making minor tweaks | Review of dashboard - in progress |  | Power BI Dashboard delivered |  | - Investigating Think Perth analytics support | - Access to GA - Meeting with DW to take through details and determine level of access required or BA dashboard development | - Looking at potential year review as part of site decoupling
Onboarding | · Elearning |  | KC completed first draft of manual |  | KR making final adjustments to manual | content owners proposed for agreement by managers of responsibility of pages. | All moudles and questions definined Video recording software secured |  | - HR delivered first draft of e-learning | - e-learning course complete and ready to go - Need tester - MQ? | - waiting for appointment of support person
| · CO and SME mapping | [5 empty] | 75% have responded |  | - complete |  | - waiting for appointment of support person
| · Documentation |  | KR reviewing along with website implementation | Site satandards workshop - Part one - completed | KC developed first two modules - For review |  | • Sitecore user Manual • Digital Content Standards • Website style guide • Website Publishing checklist |  | - Another draft of style guide with digital aspects in progress | - Style guide redraft complete - Gove doc draft one complete - to be reviewed | - waiting for appointment of support person
| · Workshops |  |  |  | Supporting documents drafted - in review |  | Four vendors contacted for quote. Three received |  | - Bang selected as vbendor -Workshops booked and most invitees have confirmed | - Complete - Mixed participation success - Need to find approach for those who didn't attend - Coordination of content strategy completion and sign offs next step | - waiting for appointment of support person
· Accessibility | · Accessibility audit – quotes to be logged in CM |  | Commenced 17 June | Completed | Presented to EL - Recommendations for further communication | Receieved videos from Web Key IT | Milestones agreed, awaiting documentation |  | - Major issues and Level A compliance on track for fixing by end of September | - Ongoing | - added into stream of 2.1 work. Now logged into Dev Ops
| · Preferred supplier to be lodged – On hold |  |  | Presentation of initial findings Thursday 4 July | Scoping with Web Key IT of video recording of tester using website
Presented to AIAG
Brand presentation - next week - pending confirmation
· Social media | · Trialing Brolly to capture social media records |  | On hold |  | Drafting inquiry social media info |  | social media plan and escalation matrix for inquiry delivered
· Library posts ongoing (with MKT)
· EXM | · Stakeholder meeting to be set up by CT |  | On hold | On Hold | On hold |  | On hold |  | - On hold | - On hold - Subscription payment on hold until fully implemented | - On hold - Subscription payment on hold until fully implemented
· Screen management | · Document reviews and recommendations in progress – On hold |  | KC and MS have reviewed the documents and combined recommendations - awaiting word version from KL | Presented to KL today - follow up on Friday for feedback | KC reformatted and drafted plan |  | Awaiting further direction from KL |  | - no current work | - no current work | - Advice sought on programming for upcoming event. Provided background and guidance
Reviewed and with KL for comments
· Draft Planning Strategy | · CPU using flip book for website |  |  | _ | -
· Phase 2 | · Website consultation sessions with Managers almost complete – to be compiled and validated. |  | All consolations complied - remaining three meetings this week | ELT presentation scheduled for Monday | ElT presentation today | Marcin to be project manager. Already in PPS | Project planning commenced Awaiting BA resource allocation from DAI |  | - AS from DAI gathering requirements - Project kick off meeting Thursday 19 Sep - Tester secured - 9.2 upgrade meetings completed | - Met with new sponsor and had team kick off meeting - Secured tester for project - met with Lloyd for endorsement of ITC staff support and resourcing for project - BA (AS) committed for 80% - Met with Brand t discuss collaboration model in agile delivery and project governance - First timebox and sprint kick off 25 Sep - Next steps decision on upgrade and brief to agency | - Timebox 1 closed out yesterday. Timebox 2 kicks off today. - Decisionson Upgrade, Site serach closed out and briefed to Brand -
Consultation with EL today
- Data app | - Concept meetings |  |  |  | Meeting with DAI this week |  |  |  |  | Met with JH, DW on concept - Smart cities - Met with CLA, LZ, JH and DW to refine concept in constraints of current inflight dev projects- Next steps summarising potential and present to BF | - Summarizing still to be completed
· Chat bot/ Virtual Assistant | · RFQ document review and panel assessment |  | Presentation 18 June |  | -
· Other
Styl labs | · Stylabs presentation – On hold |  | On `hold
Heritage Perth |  |  |  | Working group first meeting 3/7 Meeting with Crush tbc | Meeting with internal stakeholder and external agency complete |  | Support model with Crush to be finalised |  |  | - Meeting next week re website | - follow up meeting on how to approach April event to be scheduled
Drafting documentation
Campaigns | Christmas | [8 empty] | - brief with agency - Web requirements tBC | - Met with LZ on Chrsitmas - Timelines current concern
Site security and Dev | Dev environment build | [8 empty] | - DRM working with Brand and NA to build Dev environment for CoP team - Improvements in Brand approach to code repo | - Dev environment completed
Upcoming
Social
Graphic Design
CDU
| · East Perth Revitalisation |  | Draft sent |  | Draft sent | [5 empty] | Underway
| · Perth Riverfront |  | Meeting requested |  | New meeting set | [5 empty] | with CDU
· Wayfinding update
| · Public Lighting framework | [9 empty] | Print management
Community Services
| · RAP Innovate |  |  |  | Awaiting content | [5 empty] | Still pending content
| · Homeless Services brochure redesign |  |  |  | Awaiting content | [5 empty] | Still pending content
| · Homelessness Plan |  |  |  | Complete | [5 empty] | Complete
| · Community Survey | [9 empty] | Awaiting approval
| · Common Ground Homelessness brochure | [9 empty] | Complete
· Volunteer appreciation event invite and certificates
· Access and Inclusion Plan posters
· Citiplace mural sticker
· International diability day invites
· Access and Inclusion certificates
ED
| · Perth Prospectus update |  | Agreeing on timeline |  | Awaiting content - have met to discuss | [5 empty] | Complete
· Medical science display backdrop
· Gift postcards update
Business Support
| · Pridefest advert |  | Awaiting approval |  | Awaiting approval
Arts Culture and Heritage
| · Heritage Perth Weekend cover/postcard/eDM | [9 empty] | Pending approval
· Barracks Arch signage (Open House Perth)
Data and Information
· Performance Management graphics
| CCU |  |  |  |  | Inside City August
| · What's On |  | Draft completed |  | New draft completed | City of Perth News
| · Photography |  | Ongoing |  | Ongoing
Waste
| · Skyworks bin stickers | [9 empty] | Pending approval
Governance
· Kagoshima 45th anniversary
Marketing
· Brass on the Grass
| · New Year's Eve | [9 empty] | artwork signoff 18 October
| · Christmas | [9 empty] | artwork signoff 18 October
· Hello Perth advert
| · InCopy |  | Training available via Lynda.com | TE to complete InCopy training | Training available via Lynda.com
· Style guide update
· James Leave from 8-17 July
Publications, campaigns and events
· Parklets | · Parklets trail starts this week (Post newspaper story and Community news to cover) | Organising live X on Friday 4pm | Live X was a success. Evaluation report now done and shared
· Let’s Thursday | · Media kits delivered | Live X today - Goody Two's | Let's Thursday now wrapped up. Evaluation report w Brooke for review before progressing | Evaluation report complete and final is w Simone
· Media relations ongoing
· So Perth, Post newspapers, Community News.
East Perth mural |  |  |  |  | Organising photo for Perth Voice with City rep, East Perth Community Group rep and artists for mural as part of Renew Royal Street Project which uses a City art grant. | Photo is done and Perth Voice is going to publish this one pending a chat with the artist
· Winterfest | · TE working on comms plan |  | Communications plan finalised and being implemented | Media opportunities ongoing. Four live TV crosses last week + other successful coverage. More locked in. | Last week of Winter Fest - media opportunities are quietening down but did have more crosses and coverage this last week with Studio 10, WTV, etc. | Winter Fest evaluation report has been finalised and sent to relevant people and teams
|  |  | Media release and kits went out and were well received. Several oppportunities locked in already for later in June | Helping Marketing organise paid media opp (ooportunity to meet new contacts) | Cross went well and made new contact
|  |  | Completing media release on Winter Fest Theatre accesibility features. | Accessibility and inclusion release out - not much interest as of yet
|  |  | There is a risk that the hero event (Borealis) may not go ahead. Delaying preview event invite. | Borealis went ahead - last minute media night organised and was a success
|  |  |  | Going to pitch a photo opp for East Perth Communuity Group artwork - one piece is part of Winter Fest | East Perth artwork didn't work out, am working on this photo opp but no longer focussed on Winter Fest
· Skyworks 2020 |  |  | Meetings have commenced. Set-up location to change, no theme, looking likely skyshow will return (confidential for now though). TE will keep MH and HK in the loop. | No update on Skyworks | No update - consortium meeting next week | Likely new location for fireworks to be set up is South Perth. Vic Park is another option but more expensive. |  | Meeting with the Consortium tomorrow. Will look into details about re-introducing the air show and what comms we might need to do around this. |  | Channel Nine announced return of the airshow at the 2020 skyworks on Monday 23/9 | Next Skyworks consortium meeting scheduled for Thursday 24 October
|  |  | Submitting Skyworks into Australian Events Awards (Best Community Event category) and WA Tourism Awards (Major Festivals and Events category) - big potential for media release if wins. These will be in about Aug and Sept 2019. |  |  | Talked about how hyping up crowd numbers may be detrimental to attendance numbers. Need to undersell or avoid mentioing numbers before the event, then upsell afterwards. Need to promote quiter vantage points too. Agreed to stay on 300K number (this is a very rough and generous estimate but we can't go down because of risk to negative media attention)
|  |  | Tender going out for hostile vehicle mitigation plans - MH to liaise with TE on this one with regards to Skyworks. Eastern states based companies have the appropriate technology - all tenders go national. Doing all we can to ensure the safety of the community at major events e.g Skyworks. |  |  | There will be some changes to road closures and HVM plans so media may not be able to access sites as close to the action this year around. Need some alternatives.
Talked about encouraging people to stay or come into the city early to drive business. Early stages but might be a comms opportunity?
Shop in Full Colour | [5 empty] | Organising media kits (picnic basket) | Media kits done, except for labels (coming from Jake) | Media kits sent out last week along with proactive pitches and a blanket media release. |  | Perth Life live crosses by Adrian Alaberg from Sense of Spring activations the Bee Hive at Forrest Chase and Swing at 140 this morning - interviewed Tabitha and "Famous Sharron" | Campaign finishes Sunday 13 October
[6 empty] | Strategy is almost complete | Strategy complete | 6PR and Curtin FM have already requested interviews, while Channels 9 and 10 have expressed strong interest. The West and Commnity News have requested images which indicates the possiblity of stories. |  | Twilight Hawkers Markets started last Friday - live cross Beau Pearson Ch 10 (Around Town) + coverage in the West Inside Cover + Ben on 6PR
[6 empty] | Media release is almost finalised | Media release is all done apart from quote approval and event info - currently w Simone |  |  | Little Green Thumb workshops start this weekend Saturday 28 October - 4 October. Tabitha promoted on 6PR last Sat
The City at Christmas | [5 empty] | Activations are going to be really good and include: sensory experience rooms, giant dandelions, pop-up editions of Twilight Hawkers Market, etc. | Internal comms are all organised as much as can be - waiting on event/activation confirmations and details. There's going to be an internal photo comp. | Will work on Tomi's strategy to make sure internal comms go out on time. Will set up the internal photo comp when the timing is right. |  |  | With S.I.F.C finishing the week, focus shifts to Christmas. Maddie currently working on Strategy. Brooke to review next week.
· What’s On | · June edition in draft with graphics. |  | July issue at print already - Winter Fest heavy content | July edition was out early. August edition w Graphics | August edition almost ready to go. Just needs reviews and approvals. Starting Sept issue soon. | August has been printed and distributed. September graphic request will be in soon. | Sept is in approval stages - ahead of schedule | Sept arrived on Monday. Am waiting on final content from Elizabeth at the Library to send October content through to Graphics (looking at Sept 6). |  | October edition has been sent to the printers. Expected delivery earlu next week. | Maddie completed draft in Word doc, ready to send to Design today pending minor additional details. Brooke to review first mock-up next week.
· City News | · Currently drafting articles for 12 pager (June) |  | September flat lay approved | Currently writing content for Sept issue. It's looking very full. First 8-pager in a while. | Content all written, waiting for futher GM announcements and Spring in the City info before putting in graphics request later this week | Graphic request is in and just waiting on Council decisions re: 3 hour parking to update content. Everything else if ready | Spring is in approval stages - ahead of print date 28/07 | Spring has been sent to print! |  | Brooke taking Maddie through flat plan and process today for December quartlerly edition | Maddie gathering information and has started writing content for the Summer (December) edition
New contract includes 99% recycled paper - TE to include wording on this to let residents know we're addressing sustainability concerns surrounding the newsletter
· Perth City Local e-newsletter | · |  | July issue in the world | July due out 3 July. New, refreshed template. | New look EDM went out in July and performed well | August is ready to go, started September issue |  | September is almost in final approval stages with Simone (will send her a final copy once I've implemented info from ACH and parking trial story) |  | Draft to be completed today and sent for approvals | Maddie has started populating template in Mailchimp with November content
|  |  | Subscribers numbers are increasing slowly due to CTA in City News and External Comms Survey. | Subscribers continuing to increase | Met with Alyce to discuss regularly updating database using the CRM. Alyce is going to broaden her search and send an update every 3 months | Still chasing up Alyce re: new subscribers to add to the database
| · Review report and recommendations for Perth City Local - with CT for review |  | First EDM review and recommendation report approved and shared. Jan to June report in the works soon | Jan to June report finalised and sent to Simone
Parklet Trial Results |  |  |  | Communications Plan - to start soon
Meeting w AH to discuss how we can update subscribers regularly using the CRM database
· External communications survey | · In progress |  | In progress. Several submissions received. Advertising live on Facebook. Survey closes 1 July | Closed 1 July. 112 partipants (on par w last year). Waiting for summary and report through some AH before beginning work on evaluation report. | Report is done and currently under review for approvals
· Contracts for publications | · In progress | RFQ - process sorted | Quote reviewed and supplier chosen and informed. | Closed and finalised for 2019-2020 financial year.
· Publications website page |  |  | Most recent issue of each publication soon to be on News and Updates page, including CTA to subscribe | Publications and subscribe button now on website. Not final outcome but a good start to get it on there.
Speeches
|  |  | Targa West | NAIDOC Week Opening - completed | CISA - Speech Completed | Targa West - Opening | EPCSG AGM
Upcoming | [5 empty] | Targa West - Ceremony | 60th Anniversary of Council of the Ageing | BH working on this.
|  |  | YMCA |  |  | EPCSG AGM
CPP
Branding | Delivering a FAQ about paid parking |  | almost finished, waiting for approval from CPP
| Consistent Thank you campaign for events |  | Working on deliverables (Targa West first event)
| Satisfaction research CPP |  | Working on survey, live by end of this week
Partnerships | Rooftop movies |  | Council meeting 25 June
| Telethon |  | Working on council report for July
| Wildcats |  | Drafting memo for CEO for new partnership
| DoubleTree |  | Renewal
| Fourpoints |  | Working on renewal (1 July)
| Knightcorp |  | Waiting for a reply from them on renewal
| Perth Glory |  | Waiting for singned copy
| Curtin University business school |  | Signed, now organising operations
Promotions | Winterfest report signed off by ELT |  | Working on delivery, newsletter end of this week
Development of Annual plan for parking promos
| IPMS roll out |  | Roll out planned for July
Graphics | Digital screen at HM CPP |  | Aiming for install before end of month if no delays with screen at customs
| Pier Street bay counter replacement |  | Scheduled for week of 24 June
| Annual fee change signage, website information, parking guide |  | Ongoing
Miscellaneous
· DAIP |  |  | CT and BH working on Accessible Information Policy with Jen and Siobhan. BH to follow up on Siobhan. | Siobhan yet to let us know information. She will do after the policy on policies gets approved.
· Photo talent release | · CT working on Procedure and work with IM to establish recordkeeping.
· Policy review (CCU policies) |  |  | Ongoing - to go to Council in August (pending Council adoption of the 'policy for policies' in June/July meeting
· Content submission form | · DAI have reviewed and will put to TE |  | Ongoing
· LG election communications (No City election in 2019) – Governance |  | Ct to set up meeting with Gov | CT met with Gov. Gov reviewing webpage info and will send updates via web form. Text to be used from this to inform internal and external comms (Intranet announcement, PCL content, City News Sept) Using platforms so people are aware. MH to send details through to CT from minister's media advisor. | Content and basic comms checklist prepared by CT and sent to Gov for approval
Australian Event Award submission |  |  |  | Helping Louise Mayberry with Australian Event Awards entry (may need BH input because focus on Christmas Lights Trail) | This is done and submitted.
Media release for Post, will also send to Community
Policies, Procedures and Guides
* Social Media Policy and Guidelines |  |  | To go before Council in August
No update
Marketing and Comms Strategy due to be completed in April 2020 | [10 empty] | discussion paper went to Commissioners - facilitated workshop between Karin and Commissioners next week.
Inquiry Panel
· Communications Plan | * Weekly positive stories ongoing |  |  | Meeting set for
* Next meeting TBC
CT - discuss CEO involvement with Ben (vid to be completed by end of Oct) | graphic design - use of InDesign (IT)
#NAME? | Perth City Local approval